## Sheet1
Issue | Description | Story Points | Assignee | Priority | Due Date
Implement notifications for new evaluations | Create the NotificationMailer#new_evaluations_reminder method and view so that students and instructors can get notified when a new evaluation has been completed | S (2) | Gabriel S. | Medium | 2024-11-12
Implement AI Feedback Coach for Student Evaluations | Implement an AI feedback coach to generate real-time, structured feedback for student peer evaluations based on numerical ratings across four key assessment criteria. | L (5) | Luqman H. | Medium | 2024-11-12
Make static code analysis pass | Fix all files in our repository to make static code analysis pass | L (5) | Gabriel S. | Medium | 2024-11-22
Add Rubocop to run as a GitHub Action | Add a workflow for Rubocop to run on PRs Make sure this workflow runs before the CI workflow | S (2) | Gabriel S. | High | 2024-11-23
Implement Team View, Edit, and Create Logic (Students) | Develop both the view and back-end logic for students to view their team, edit team details (name, description), and create a new team if not part of one. | M (3) | Gabriel S. , Kourosh F. | Low | 2024-11-24
Add AI-Powered Learning Insights Feature | We need to implement personalized learning insights for students based on their peer evaluation data. This feature will help students get actionable feedback and track their progress over time. | L (5) | Luqman H. | Medium | 2024-11-24
Automatic Team and Evaluation Management | Implement features to enhance project and team management for instructors and students. This includes adding date constraints for projects and teams, automating evaluation creation when students join teams, and ensuring evaluations are dynamically updated as team memberships change. | M (3) | Luqman H. | High | 2024-11-25
Make Navbars and Backgrounds Float (Student + Instructor) | Make sure that the navbars for both student and instructor dashboards take the full height of the screen and stay in place when scrolling, giving the illusion that they are "floating". Do the same thing for the background image in both dashboards, ensuring it is "floating" and always in the same place when scrolling. | S (2) | Yassine H. | Medium | 2024-11-25
Implement Dismissible Toasts | Create four new toasts: success.html.erb error.html.erb info.html.erb warning.html.erb Yield them in the main application view (app/views/layouts/application.html.erb), in between the navbar and the content. Replace all flash[:notice] in the source code with flash[:success] Replace all flash[:alert]in the source code with flash[:error] Make sure all toasts have a 'x' button and upon being pressed, it dismisses the toast Make sure that if the close button is not pressed, the toast fades out automatically after 10 seconds | S (2) | Daniel A. | Medium | 2024-11-25
Fix All Specs | Make sure that when u run 'bundle exec rspec .' all tests pass | M (3) | Gabriel S. | High | 2024-11-25