## Sheet1
Issue | Issue # | Description | Epic | User Story | Story Points | Assignee | Priority | Due Date
Update the instructor dashboard's Results Figma Design | #97 | The instructor dashboard's results page should list all of the selected_course's students in a table, each with the following information: Student ID, Last Name, First Name, Cooperation, Conceptual contribution, Practical contribution, Work Ethic, Average, # of evaluations received, and actions. Under actions, each row should have a link to 'see detailed view', which will represent a new Detailed Results View page. | EPIC#3 | - | S (2) | Daniel A. | High | 2024-11-07
Redesign Student Dashboard's Overall Scores | #100 | Redesign the student dashboard's overall scores to display each score out of 7. Also, add a gradient colour code to the score boxes. Acceptance Criteria Add 'Overall Scores' subtitle Display all scores out of 7.00, and make them bold. Display all scores on a colour gradient, where a score of 0.00 will give #bd2611 (red), and a score of 7.00 will give #028f00 (green). | EPIC#2 | - | S (2) | Daniel A. | Medium | 2024-11-03
Implement Evaluations Due Notifications | #107 | Implement a feature to send notification emails to students when they have one or more evaluations with the status pending and a due date of tomorrow. Utilize the new NotificationMailer to accomplish this task. The notification should remind students about their upcoming evaluations and include relevant details such as the number of pending evaluations, course name, and project name. | EPIC#4 | US#9 | M (3) | Gabriel S. | High | 2024-11-08
Customize Notification Mailer | #108 | Customize NotificationMailer#evaluation_reminder so that it can be reused for sending various types of notifications. This mailer should be designed to provide consistency across different types of emails sent from our system. | EPIC#4 | US#8, US#9 | M (3) | Luqman H. | High | 2024-11-09
Update Settings Page for Instructors and Students | #86 | Update the User model to have birth_date, and profile_picture fields, as well as updatung settings page for Users to be able edit their birthday, and profile picture. | EPIC#2, EPIC#3 | - | M (3) | Luqman H. | Medium | 2024-10-28
Implement Leave Team and Join Team Functionality (Students) | #64 | Develop the logic to allow students to leave their current team or join an existing team. | EPIC#1 | US#7 | M (3) | Gabriel S. | Low | 2024-11-04
CRUD + Add maximum_team_size to projects (Instructors) | #88 | Give Instructors the ability to Create, Read, Update and Delete (CRUD) Projects. Additionally, add the maximum_team_size field to projects, which has a default value of 6. | EPIC#3 | US#2 | M (3) | Kourosh F. | Medium | 2024-10-28
Add student_id to Users | #96 | Add the student_id field to users, allowing students (not instructors) to sign up with a required student_id field. | EPIC#2, EPIC#3 | - | M (3) | Ahmad S. | Medium | 2024-10-29
Update the Instructor Dashboard's Results | #98 | Update the instructor dashboard's results view and controller to match the new Figma Design. This includes displaying a table with every student in the course, listing their Student ID, Last Name, First Name, Cooperation, Conceptual contribution, Practical contribution, Work Ethic, Average, # of peers who responded, and a link to 'see detailed view'. Implement the detailed view page and add a method for it in the controller. | EPIC#3 | - | M (3) | Yassine H. | Medium | 2024-11-04
Implement Team View, Edit, and Create Logic (Students) | #63 | Develop both the view and back-end logic for students to view their team, edit team details (name, description), and create a new team if not part of one. | EPIC#2 | US#6 | M (3) | Gabriel S. | Low | 2024-11-08
Total |  |  |  |  | 28